## Sheet1
Planning week 3, 4 & 5 sm4
| Maandag |  | Dinsdag |  | Woensdag |  | Donderdag |  | Vrijdag
| 09:00 - 12:00 | 13:00 - 16:00 | 09:00 - 12:00 | 13:00 - 16:00 | 09:00 - 12:00 | 13:00 - 16:00 | 09:00 - 12:00 | 13:00 - 16:00 | 09:00 - 12:00 | 13:00 - 16:00
Week 3 | Showcase progress to Arjan and Luuk, process feedback, create first iteration of low fidelity prototype | finish working on low fidelity prototype (wireframes/paper prototype), test prototype (user test), write report on tests | Research technical solutions MVP | Finish research on technical solutions, Work on MVP | Work on MVP | Work on MVP, Prepare demo for Xuemei | Demo product/prototype to Xuemei, process feedback | Work on MVP | Work on MVP | Showcase progress to Arjan and Luuk (UX, portfolio, code)
Week 4 | Showcase progress to Arjan and Luuk, process feedback | Create medium fidelity prototype (Figma, design), test prototype (usability/guerilla test), write report on tests | Work on MVP (if necessary: research alternative solutions) | Work on MVP | Work on MVP | Work on MVP, Prepare demo for Xuemei | Demo product/prototype to Xuemei, process feedback | Work on MVP | Usability test MVP on others than PO | Showcase progress to Arjan and Luuk (UX, portfolio, code)
Week 5 | Showcase progress to Arjan and Luuk, process feedback | Work on MVP | Work on MVP finishing touches/final adjustments/final additions | Work on MVP finishing touches/final adjustments/final additions | finalize MVP demo app | Work on MVP, Prepare demo for Xuemei | Demo product/prototype to Xuemei, process feedback | Work on portfolio | Work on portfolio | Showcase progress to Arjan and Luuk (UX, portfolio, code)
Every week serves as an iteration